## Sheet1
Week | <component> |  | Time Estimation
2023-01-06 | create project estimation sheet |  | 1
2023-01-06 | create Trello board |  | 1
2023-01-06 | Set Up Azure Cloud Shell |  | 2
2023-01-06 | CI: Configure GitHub Actions |  | 1
2023-01-06 | Continuous Delivery on Azure |  | 3
2023-01-09 | Documentation |  | 1
2023-01-09 | Demo Video |  | 3
2023-01-10 | Check Project Work |  | 1
2023-01-10 | Submit Project |  | 0.5
| Goals | Goals
Project Plan
Setup Project
CI Pipeline
CD Pipeline
Documentation